## Summary
PROGRAM RAID LOG
Program Name
TPM
Version | 1.0
Last Updated
RAID STATUS SUMMARY
Category | Total Items | Open | In Progress | Closed / Resolved | No Owner | No Plan | Notes
Risks | [6 empty] | Closed counts Mitigated + Closed. No Plan = blank Mitigation Plan.
Assumptions |  |  | n/a |  |  | n/a | Closed counts Validated, Invalidated and Closed. Assumptions have no in-progress state.
Issues | [6 empty] | Closed counts Resolved + Closed. No Plan = blank Resolution Plan.
Dependencies | [5 empty] | n/a | Open = On Track; In Progress = At Risk + Blocked. No owner = blank Owner (Our Side).
HOW TO USE THIS LOG
1. Fill in Program Name, TPM, and Last Updated at the top of this sheet.
2. Each tab covers one RAID category. Start every program by running a team session to populate the initial list.
3. Review the log on a regular cadence - weekly for fast-moving programs, bi-weekly for steadier ones.
4. Every item needs an owner. An item without an owner is not being managed.
5. Close items when resolved. A closed item with a resolution note is more useful than a deleted one.
6. Escalate early. The log is your early warning system - use it before problems become crises.
Counts include only rows with a description. Item IDs are prefilled, so an empty row is not an item.

## Risks
RISK LOG
Risk ID | Description & Impact | Owner | Category | Probability | Impact | Risk Rating | Proximity | Status | Strategy | Mitigation Plan | Date Raised | Target Close | Date Closed | Days Open | Notes
Categories: Technical ¦ Schedule ¦ Budget ¦ Operational ¦ External ¦ Probability & Impact: High / Medium / Low ¦ Status: Open / In Progress / Mitigated / Closed ¦ Strategy: Avoid / Mitigate / Transfer / Accept ¦ Risk Rating = Probability x Impact (Low 1, Medium 2, High 3): 6-9 high, 3-4 medium, 1-2 low
R1
R2
R3
R4
R5
R6
R7
R8
R9
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
R41
R42
R43
R44
R45
R46
R47
R48
R49
R50
R51
R52
R53
R54
R55
R56
R57
R58
R59
R60
R61
R62
R63
R64
R65
R66
R67
R68
R69
R70
R71
R72
R73
R74
R75
R76
R77
R78
R79
R80
R81
R82
R83
R84
R85
R86
R87
R88
R89
R90
R91
R92
R93
R94
R95
R96
R97
R98
R99
R100
Formulas:
Days Open = IF([Date Raised]="","",IF([Date Closed]<>"",[Date Closed]-[Date Raised],TODAY()-[Date Raised]))

## Assumptions
ASSUMPTIONS LOG
ID | Assumption Description | Status | Reason / Basis | Validation Action | Impact if Wrong | Owner | Date Raised | Date Closed | Notes
Status options: Open ¦ Validated ¦ Invalidated ¦ Closed ¦ Log an assumption any time you are treating something as true without confirmation. If it turns out to be wrong, would it change the plan? If yes, write it down.
A1
A2
A3
A4
A5
A6
A7
A8
A9
A10
A11
A12
A13
A14
A15
A16
A17
A18
A19
A20
A21
A22
A23
A24
A25
A26
A27
A28
A29
A30
A31
A32
A33
A34
A35
A36
A37
A38
A39
A40
A41
A42
A43
A44
A45
A46
A47
A48
A49
A50

## Issues
ISSUES LOG
Issue ID | Description & Impact | Owner | Category | Priority | Status | Resolution Plan | Date Raised | Target Resolution | Date Closed | Days Open | Linked Risk ID | Notes
Categories: Technical ¦ Schedule ¦ Budget ¦ Operational ¦ External ¦ Priority: High / Medium / Low ¦ Status: Open / In Progress / Resolved / Closed ¦ A risk that happened is an issue. Name it what it is.
I1
I2
I3
I4
I5
I6
I7
I8
I9
I10
I11
I12
I13
I14
I15
I16
I17
I18
I19
I20
I21
I22
I23
I24
I25
I26
I27
I28
I29
I30
I31
I32
I33
I34
I35
I36
I37
I38
I39
I40
I41
I42
I43
I44
I45
I46
I47
I48
I49
I50
I51
I52
I53
I54
I55
I56
I57
I58
I59
I60
I61
I62
I63
I64
I65
I66
I67
I68
I69
I70
I71
I72
I73
I74
I75
I76
I77
I78
I79
I80
I81
I82
I83
I84
I85
I86
I87
I88
I89
I90
I91
I92
I93
I94
I95
I96
I97
I98
I99
I100
Formulas:
Days Open = IF([Date Raised]="","",IF([Date Closed]<>"",[Date Closed]-[Date Raised],TODAY()-[Date Raised]))

## Dependencies
DEPENDENCIES LOG
Dep ID | Description | Type | What We Need | Owner (Our Side) | External Contact | Due Date | Impact if Late | Likelihood | Impact | Status | Notes
Type: Internal / External ¦ Status: On Track / At Risk / Blocked / Complete ¦ Every dependency needs an owner on your side and a contact on the other side. 'I haven't heard back' is not a status.
D1
D2
D3
D4
D5
D6
D7
D8
D9
D10
D11
D12
D13
D14
D15
D16
D17
D18
D19
D20
D21
D22
D23
D24
D25
D26
D27
D28
D29
D30
D31
D32
D33
D34
D35
D36
D37
D38
D39
D40
D41
D42
D43
D44
D45
D46
D47
D48
D49
D50